## Progress with Graph
GANTT CHART
| Project Title |  | DC Variable Voltage Power Supply |  |  |  |  | Company Name | JAC EngTech
| Project Manager |  | Hana Chammas |  |  |  |  | Date | 2021-09-23
← ←[Hide these 3 Rows) ← | [Enter WBS#] ↓ | [Change Task Title] ↓ | [Enter Start Date] ↓ | [Enter Due Date] ↓ | [Do not Enter any value Here] ↓ | [Enter Days Completed] ↓ | [Do not Enter any values here] ↓ | [Do not eneter values here] ↓
| WBS # | Task Title | Start Date | Due Date | Duration | Days Completed | Days Left | % of Task Complete
| 1 | Develop Circuit
| 1.1 | Read LM317 Datasheet | 2021-08-30 | 2021-09-01 | 1 | 1 | 0 | 100%
| 1.2 | Calculate any necessary values (power ratings, resistors, etc.) for BOM | 2021-09-01 | 2021-09-04 | 3 | 3 | 0 | 100%
| 1.3 | Make a BOM from LM317 Datasheet | 2021-09-01 | 2021-09-04 | 3 | 3 | 0 | 100%
| 1.4 | Design Circuit Schematic on DipTrace | 2021-09-04 | 2021-09-12 | 8 | 8 | 0 | 100%
| 1.5 | Components | 2021-09-04 | 2021-09-14 | 10 | 10 | 0 | 100%
| 1.6 | Printing and Soldering | 2021-09-11 | 2021-09-21 | 10 | 10 | 0 | 100%
| 2 | Box
| 2.1 | Design Box Layout | 2021-09-21 | 2021-09-28 | 7 | 7 | 0 | 100%
| 2.2 | Create 3D Model | 2021-09-28 | 2021-10-05 | 7 | 7 | 0 | 100%
| 2.3 | Fold Box | 2021-10-05 | 2021-10-12 | 7 | 21 | -14 | 300%
| 2.4 | Fit Components | 2021-10-12 | 2021-10-19 | 7 | 10 | -3 | 142.9%
| 2.5 | Ground Case | 2021-10-12 | 2021-10-19 | 7 | 10 | -3 | 142.9%
| 3 | Extra
| 3.1 | Sanding and Painting | 2021-10-19 | 2021-11-03 | 14 | 10 | 4 | 71.43%
| 3.2 | Trouble Shooting | 2021-11-03 | 2021-11-24 | 21 | 21 | 0 | 100%
| 3.2 | Manual | 2021-11-24 | 2021-12-15 | 21 | 19 | 2 | 90.48%